## Product Backlog
Project Name | OpenCart(Fronted)
Client | OpenCart
Created By | Name of Product Owner
Creation Date | 2026-03-03
approval Date | XX/XX/XXXX
Epic | User Story ID | Feature / Title | User Story | Status | Acceptance Criteria
EPIC-01 User Account Management | US-001 | Register Account | As a new customer, I want to register an account so that I can use customer account features. | New | User can enter required details, validation messages are displayed for invalid data, and a valid registration creates an account.
| US-002 | Login | As a registered customer, I want to log in so that I can access my account. | New | Valid credentials allow login; invalid credentials show an appropriate error message.
| US-003 | Logout | As a logged-in customer, I want to log out so that my account remains secure. | New | User can log out successfully and protected account pages cannot be accessed without login.
| US-004 | Forgot Password | As a customer, I want to reset my forgotten password so that I can regain access to my account. | New | User can request password reset using a registered email and receives appropriate reset instructions.
| US-005 | Account Information | As a customer, I want to update my account information so that my personal details remain current. | New | Customer can view, edit and save valid account information.
| US-006 | Change Password | As a customer, I want to change my password so that I can maintain account security. | New | Current password is validated, new password rules are applied, and matching confirmation is required.
| US-007 | Address Book | As a customer, I want to manage my addresses so that I can use them for orders. | New | Customer can add, edit, delete and manage valid addresses.
EPIC-02 Product Discovery | US-008 | Product Search | As a customer, I want to search for products so that I can quickly find the product I need. | New | Valid keywords return relevant products; invalid/blank searches display appropriate results or messages.
| US-009 | Product Compare | As a customer, I want to compare products so that I can choose the most suitable product. | New | Customer can add products to comparison and view their relevant details side by side.
| US-010 | Product Display | As a customer, I want to view product details so that I can make a purchase decision. | New | Product name, image, price, availability and applicable details are displayed correctly.
EPIC-03 Shopping Cart & Wishlist | US-011 | Add to Cart | As a customer, I want to add products to my cart so that I can purchase them. | New | Selected product is added to the cart with correct product information and quantity.
| US-012 | Wishlist | As a customer, I want to add products to my wishlist so that I can save products for later. | New | Customer can add and remove products from wishlist and view saved products.
| US-013 | Shopping Cart | As a customer, I want to manage my shopping cart so that I can review products before checkout. | New | Cart displays selected products, quantities, prices and totals correctly; customer can update/remove products.
EPIC-04 Checkout & Orders | US-014 | Checkout | As a customer, I want to complete checkout so that I can place an order. | New | Customer can review cart, enter required information, select applicable shipping/payment options and confirm the order.
| US-015 | Order History | As a customer, I want to view my order history so that I can track previous orders. | New | Previous orders are displayed with relevant order information.
| US-016 | Order Information | As a customer, I want to view order details so that I can review a specific order. | New | Customer can open an order and view products, quantities, prices and applicable order details.
| US-017 | Order Return | As a customer, I want to return an eligible order so that I can request a return. | New | Customer can select an eligible order/product and submit a valid return request.
EPIC-05 Customer Order Services | US-018 | Downloads | As a customer, I want to access my available downloads so that I can download purchased digital products. | New | Available downloads are displayed and accessible according to the customer's orders/account.
| US-019 | Reward Points | As a customer, I want to view my reward points so that I can track my available points. | New | Applicable reward point information is displayed correctly.
| US-020 | Return Requests | As a customer, I want to view my return requests so that I can track their status. | New | Submitted return requests are displayed with relevant status/details.
| US-021 | Transactions | As a customer, I want to view my transactions so that I can track account transactions. | New | Applicable transaction records are displayed correctly.
| US-022 | Recurring Payments | As a customer, I want to view/manage recurring payments so that I can track recurring payment information. | New | Applicable recurring payment information is displayed and relevant actions work correctly.
EPIC-06 Product & Store Features | US-023 | Product Review | As a customer, I want to submit a product review so that I can share my product experience. | New | Customer can submit valid review information and appropriate validation is applied.
| US-024 | Currencies | As a customer, I want to change the currency so that I can view prices in my preferred currency. | New | Available currencies can be selected and applicable product prices update correctly.
| US-025 | Contact Us | As a customer, I want to contact the store so that I can submit my enquiry. | New | Customer can enter required contact information, submit the enquiry and receive appropriate confirmation/validation.
EPIC-07 Common UI & Navigation | US-026 | Home Page | As a customer, I want to access the home page so that I can navigate through the store. | New | Home page loads correctly and major elements such as logo, navigation, search and product categories are available.
| US-027 | Header, Footer & Menu | As a customer, I want to use the header, footer and menus so that I can navigate the application easily. | New | Header, footer and menu links are displayed correctly and navigate to the expected pages.

## Sprint Meeting
Project Name | OpenCart(Frontend)
Client | OpenCart
Created By | Name of Scrum master
Attendence | Scrum Team
Creation Date | XX/XX/XXXX
Epic | User Story ID | Feature / Title | User Story | Story Point | Sprint
User Account Management | US-001 | Register Account | As a new customer, I want to register an account so that I can use customer account features. | 5 | 1
| US-002 | Login | As a registered customer, I want to log in so that I can access my account. | 3 | 1
| US-003 | Logout | As a logged-in customer, I want to log out so that my account remains secure. | 2 | 1
| US-004 | Forgot Password | As a customer, I want to reset my forgotten password so that I can regain access to my account. | 5 | 1
| US-005 | Account Information | As a customer, I want to update my account information so that my personal details remain current. | 3 | 1
| US-006 | Change Password | As a customer, I want to change my password so that I can maintain account security. | 3 | 1
| US-007 | Address Book | As a customer, I want to manage my addresses so that I can use them for orders. | 5 | 1
Product Discovery | US-008 | Product Search | As a customer, I want to search for products so that I can quickly find the product I need. | 5 | 2
| US-009 | Product Compare | As a customer, I want to compare products so that I can choose the most suitable product. | 3 | 2
| US-010 | Product Display | As a customer, I want to view product details so that I can make a purchase decision. | 3 | 2
Shopping Cart & Wishlist | US-011 | Add to Cart | As a customer, I want to add products to my cart so that I can purchase them. | 5 | 2
| US-012 | Wishlist | As a customer, I want to add products to my wishlist so that I can save products for later. | 3 | 2
| US-013 | Shopping Cart | As a customer, I want to manage my shopping cart so that I can review products before checkout. | 5 | 2
Checkout & Orders | US-014 | Checkout | As a customer, I want to complete checkout so that I can place an order. | 8 | 3
| US-015 | Order History | As a customer, I want to view my order history so that I can track previous orders. | 3 | 3
| US-016 | Order Information | As a customer, I want to view order details so that I can review a specific order. | 3 | 3
| US-017 | Order Return | As a customer, I want to return an eligible order so that I can request a return. | 5 | 3
Customer Order Services | US-018 | Downloads | As a customer, I want to access my available downloads so that I can download purchased digital products. | 3 | 3
| US-019 | Reward Points | As a customer, I want to view my reward points so that I can track my available points. | 3 | 3
| US-020 | Return Requests | As a customer, I want to view my return requests so that I can track their status. | 3 | 3
| US-021 | Transactions | As a customer, I want to view my transactions so that I can track account transactions. | 3 | 4
| US-022 | Recurring Payments | As a customer, I want to view recurring payment information so that I can track recurring payments. | 5 | 4
Product & Store Features | US-023 | Product Review | As a customer, I want to submit a product review so that I can share my product experience. | 3 | 4
| US-024 | Currencies | As a customer, I want to change the currency so that I can view prices in my preferred currency. | 3 | 4
| US-025 | Contact Us | As a customer, I want to contact the store so that I can submit my enquiry. | 3 | 4
Common UI & Navigation | US-026 | Home Page | As a customer, I want to access the home page so that I can navigate through the store. | 3 | 4
| US-027 | Header, Footer & Menu | As a customer, I want to use the header, footer and menus so that I can navigate the application easily. | 3 | 4
Story Point | Hours
1 | 1 hour/1 Day (Depend on company)
0,1,1,2,3,5,8 | Fibinaccies series

## Task
Developer Task | QA Task
Under standing Requrements | Under standing Requrements
Designing | Writing Test Scenario
Coding | Writing Test Cases
Unit Tesing | Test Case Reviews
Integration Testing | Test Data Preparation
Code Review | Test Environment Setup
Bug Fixes | Test Execution
Team Meeting | Re-Testing
Any Other…........ | Team Meetings
Automation
Any Other…........